## Slide 1
Late Sprint Closure and Unfinished Scope in Scrum
Evidence from reconstructed Jira histories
Eight TAWOS projects | 2,602 modeled sprints
Hani AbuSharkh | Maryam Hanif | Rafat Damseh
Sprint analytics | TAWOS
1

## Slide 2
The problem
Risk is easiest to influence before the sprint is already in trouble.
Scrum reality
Teams usually notice risk through burndown charts, blockers, and Daily Scrum discussions after work has started.
Research question
Can reconstructed sprint-start Jira data rank these two outcomes before execution begins?
Practical caution
The analysis is retrospective. Operational benefit would need a prospective evaluation with real teams.
Sprint analytics | TAWOS
2

## Slide 3
From repository history to a sprint-start snapshot
Sprint and Story Points are rolled back to the state recorded at each sprint start.
Raw TAWOS
2,657 sprint rows
Observed outcomes
2,610 eligible CLOSED sprints
Cold-start rule
2,602 modeled sprints
Scope history
145,309 issues + 88,364 changes
Sprint-start scope
20,603 commitments
Issues created after the start, or already resolved before it, are excluded from committed scope.
Sprint analytics | TAWOS
3

## Slide 4
Two different outcomes
The two outcomes describe different repository events.
Late sprint closure
Jira records the sprint as completed more than one day after its planned end date. This is an administrative closure outcome, not a direct measure of when all work finished.
Scope spillover
At least one issue that belonged to the sprint at the start is not resolved by the planned end date. This is a narrow unfinished-scope outcome, not all forms of project risk.
Sprint analytics | TAWOS
4

## Slide 5
Main result
Late closure is moderate. Unfinished scope is easier to rank, but simple scope variables explain most of the signal.
Chart: 
| Late closure RF | Full spillover XGB | Nonempty spillover XGB
ROC-AUC | 0.705 | 0.988 | 0.862
Late closure
Moderate discrimination; project and time variation remain important.
Full spillover
Very high AUC, but helped by zero-scope sprints.
Nonempty spillover
More realistic task; still clearly above chance.
Sprint analytics | TAWOS
5

## Slide 6
How the result was stress-tested
The same conclusion is checked against time, project, provenance, and leakage assumptions.
Scope-only baseline
Tests whether larger starting scope alone explains spillover risk.
Cluster uncertainty
Uses project-aware intervals rather than treating all sprints as independent.
Rolling splits
Checks whether results depend too much on one 70/30 cutoff.
Provenance audit
Shows observed history versus static fallback by project.
Permutation importance
Evaluates feature value on held-out data.
Calibration bins
Shows how predicted probabilities behave across risk bands.
Sprint analytics | TAWOS
6

## Slide 7
Scope-only baseline
The transparent baseline is one of the strongest findings.
Chart: 
| Always positive | Scope-only LR | Random Forest
ROC-AUC | 0.5 | 0.885 | 0.852
Interpretation
For nonempty-sprint spillover, a transparent scope-only logistic model ranks risk at least as well as the heavier RF model by AUC. The contribution is therefore not “complex ML is always better.” It is that careful reconstruction reveals what signal is really present.
Sprint analytics | TAWOS
7

## Slide 8
Uncertainty and stability
The broad pattern is stable, but the uncertainty is visible.
Late closure RF
AUC .705
Cluster 95% CI: .596-.786
Rolling split AUC: .669-.711
Nonempty spillover RF
AUC .852
Cluster 95% CI: .774-.911
Meaningful but not perfect
Cross-project transfer
LOPO reports project denominators and positives. Results vary, so deployment should be locally validated.
Sprint analytics | TAWOS
8

## Slide 9
Where the evidence stops
The repository history supports ranking, not a claim of deployment benefit.
• Late closure is a Jira closure proxy, not direct proof of late work.
• Zero-scope sprints make full-population spillover easier.
• Static fallback is an identification assumption when Sprint or Story Points history is missing.
• LOPO uses local historical features from the held-out project.
• A prospective study is needed before claiming that showing scores improves planning decisions.
Safe conclusion
Reconstructed sprint-start data contain useful risk-ranking signal, especially for unfinished scope. The model is not presented as a deployment-ready decision system.
Sprint analytics | TAWOS
9

## Slide 10
Reproducible research package
The papers, result files, code, and teaching documents point to the same saved outputs.
• 6-page conference paper and supporting analysis package
• Week 14 results analysis and independent reproduction guide
• Python code, tests, result CSV/JSON files, and version lock
• Beginner learning guide and rebuild-from-scratch manual
• Presentation using the same headline metrics as the manuscripts
Use the Week 12 project folder to rerun the analysis.
Sprint analytics | TAWOS
10